## 20161220
# | Findings | Detail | Delta force reply | Update Sprint
1 | Disconnect” error after idle for a couple rounds. | After we pressed “Yes” at the error, the lobby become empty. For comparison, the image below is the notification for idling at Live Baccarat Flash version. | Issue .Fixed on UAT | Sprint 3
2 | Confirm, Undo and Clear button are enabled without placing a bet yet. |  | Issue .Fixed on UAT | Sprint 1
3 | No “Top Up” function at Live Baccarat HTML5 | For Comparison, the image below is the Top Up function at Live Baccarat Flash Version | Not yet implemented Alaredy in prodct backlog
4 | Rebet' button is disable during 'Betting Open' |  | Issue .Fixed on UAT | Sprint 3
5 | Double' button is disable |  | Issue .Fixed on UAT | Sprint 3
6 | Playing from 'Tablet' to 'Desktop' the game is not automatically open. | Steps to Replicate: 1. Login to 'Tablet' devices 2. Sit in any table then play a round 3. After a round 'Login' to desktop (Don't log off the Tablet) 4. Go to the same table and see one of the seat are disable | Means should have support multi table . Due to current Tablet version not support multi tablet We may not support the multi table at beginning. | Sprint 1
7 | Announcement always appears | Image below shows the announcement at Lobby. After we clicked the close button (X) and sit on a table, the announcement appears again. | Issue .Fixed on UAT The production "Didmiss all messages" behavior would no display after go in to inGame or go back to lobby | Sprint 1
8 | Sound and music havn't implemented |  | Not yet implemented Alaredy in prodct backlog
9 | The Baccarat bet detail can't display on tablet device |  | Implemented on UAT | Sprint 1

## 20161227
# | Findings | Detail | Delta force reply | Update Sprint
1 | No pop up message appears when dealer currently shuffling a shoe. |  | Issue .Fixed on UAT | Sprint 3
2 | No pop up message appears for unconfirmed bets. |  | Top up future yet implemented Alaredy in prodct backlog
3 | No Log off message appears after clicking shuffle button from the live dealer client. |  | Not yet implemented Alaredy in prodct backlog
4 | A disconnect pop up message appears when the table is closed. |  | Issue .Fixed on UAT | Sprint 3
5 | No message appears when Switch Dealer button were click on the Live dealer client apps. |  | Issue .Fixed on UAT | Sprint 3
6 | Enhance the behavior of the buttons on the live casino lobby. (It looks like it is disable) |  | Issue .Fixed on UAT | Sprint 2
7 | The text and the animation doesn't sync each other. |  | Issue .Fixed on UAT | Sprint 3
8 | Align the text in the center of the modal. |  | Issue .Fixed on UAT | Sprint 3
9 | Enhance the display of confirmation of bets. the modal is too big while the text is too small |  | Issue .Fixed on UAT | Sprint 3
10 | Min and Max tool tip though there is no bet has been placed yet. |  | Issue .Fixed on UAT | Sprint 3
11 | Win amoun doesn't have decimal. | currently, on the flash version of Live Casino. when system display the win amount. it used this format: #,###.## | Issue .Fixed on UAT | Sprint 3
12 | Add a auto hide function when dealing phase already started. it covers the Player Score |  | The behavior same with desktop version on production. Will consider this suggestion. | Sprint 1
13 | "You currently have confirmed bet." message appears though I don't have bets placed. | this happen when I try to exit the game. | Issue .Fixed on UAT | Sprint 2
14 | Dealer's name were not placed in the center of the Dealer Name Box. |  | Issue .Fixed on UAT | Sprint 3
15 | Aborted round - the cards stucked on the game UI. |  | Issue .Fixed on UAT | Sprint 3
16 | Incomplete message when the round is aborted. |  | Issue .Fixed on UAT | Sprint 3
17 | It doesn't close the table when the table is closed. | once the round is aborted then the table were closed, the player should be redirected to Live Casino lobby. | Issue .Fixed on UAT | Sprint 3
18 | Full screen button doesn't function as it was designed to do. | Only for iPad | The original tablet version does not have full screen feture, but the desktop version has full screen feature . We would like to have one version of application for both tablet and desktop, but iOS does not support full screen on chrome and Safari. Therefore, we leave the issue for now and will decide what to do when we have an idea of how users behave on production. | Sprint 3
19 | No Dealer's voice | >when betting open. >Betting is closing >Betting is closed >Player and Banker's score >Announcement of Winning hand. | Same with 20161220#8 issue Not yet implemented Alaredy in product backlog | Sprint 1
20 | System still accepts bet after betting timer becomes Zero. | wait until betting time become zero then confirmed your bet. as on the current live casino system will reject this bet but on HTML5 still accepts | Issue .Fixed on UAT | Sprint 3
21 | Other player's display name still clear up after changing its seat position. |  | Issue .Fixed on UAT | Sprint 2
22 | System doesn't load the previous table that player have seated. |  | Not yet implemented Alaredy in prodct backlog

## 20170113
# | Findings | Detail | Delta force reply | Update Sprint
1 | Chips placed on the table and Win Animation will only disappear when the new round start. |  | Issue .Fixed on UAT | Sprint 3
2 | It only display a error code when bet is confirmed when the round will start to draw a card. |  | Issue .Fixed on UAT | Sprint 3
3 | Unable to place a bet after error 301 appears or after confirming a bet that becomes zero. |  | Issue .Fixed on UAT | Sprint 3
4 | "You currently have confirmed bet" message appear when player tried to return to lobby. | this occurs when error 301 appears | Issue .Fixed on UAT | Sprint 3
5 | Betting on BANKER hand and when its win, it changes the player balance. | 1. Sit in a baccarat table. 2. Once the betting is open, Place a bet either Banker or Player Hand. 3. Refresh the game UI. 4. Player's balance will become zero. 5. If bet wins, it will the current player's balance on the game UI. 6. If Lose, player unable to bet as it will only display zero balance. | Issue .Fixed on UAT | Sprint 3
6 | It displays Zero Balance though player has sufficient Balance. |  | Issue .Fixed on UAT | Sprint 3
7 | When original balance appears and try to bet, "Your order exceeds your balance" messafe appear. |  | Issue .Fixed on UAT | Sprint 3
8 | Deactivate the chips navigation button when its reached the last option. |  | Not yet implemented Alaredy in prodct backlog

## 20170124
# | Findings | Detail | Delta force reply | Update Sprint
1 | Dealer's name doesn't fit on the lobby info. |  | Display issue will fix it.
2 | Betting area Min Max pop up doesn't follow when jumping to different betting area. |  | This issue may cause by tablet performance issue . We will have more investigate it.
3 | Suggestion . Add an effects on the side of the chips when selected. |  | This suggestion will put in product backlog
4 | Unable to place a bet on the next round after confirming the previous bet on 0 second time. | All betting control buttons were disabled. | Crucial issue . Will fix it first.
5 | 20161227 - #13 this isssue still exist | 20161227 - #13 "You currently have confirmed bet." message appears though I don't have bets placed. this happen when I try to exit the game. | Crucial issue . Will fix it first.